## Sheet1
Project | rs-ai
Start Date | 2014-05-19
Finish Date | 2014-08-25
Scale | Weeks
Task key | Colour | Description
Define/Plan |  | Create system documentation required to build the feature
Build |  | Build the feature following the documentation. Tests will be done as the feature is developed
Finalize |  | Finish system documentation and document the code
Work on/Do |  | Work on the task and finish it in the defined time period
Project Stages key | Colour | Description
Finalize |  | Finish and polish all documentation. Make sure everything has been done. Document all code
Testing |  | By this stage the AI should be finished. The final solution will now be extensively tested.
Task | Week
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Project Stage | Plan. Build. Test. Finalize. Document code. Review. | [9 empty] | TESTING
Problem Definition
Gantt Chart
Feasibility Study
AI Modes
Idle Mode
Fill Vials
Walking
Detect Banker
Detect Fountain
Interfaces
Soften Clay
Modify for clay
Drop Party
Library - Core
Mouse
Keyboard
Library - Functions
Minimap Walking
OCR
Screen Walking
Follow Player
Library - Interfaces
Lobby
Inventory
Minimap
Main Screen
Bank
Production
Lodestone
Chatbox
Trade
Emote
Clan Chat
Friends Chat
AI Commander
Commands
GUI
Account Manager
Server Manager
Network
Setup AI
Statistics
Collect and store data
Commit data to GitHub
Display statistics on site
User Documentation
User manual
AI Troubleshooting
Online Help
Wiki
Client Meetings